## 9-16 - 9-22
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
| User Story 01 * |  | User Story 01
User Story 02 |  |  | User Story 02

## 9-23 - 9-29
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
| User Story 01 * |  | User Story 01
User Story 03 |  |  | User Story 02
| User Story 02 * |  | User Story 03
User Story 04 |  |  | User Story 04
User Story 05
User Story 05 |  |  | User Story 06
User Story 09
User Story 06
User Story 09
* Completed the CRC cards and Class diagrams for User Story 01 and User Story 02.

## 9-30 - 10-6
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
As a user, I want to register to the system |  |  | As a user, I want to register to the system
As a user, I want to sign in to the system. |  |  | As a user, I want to sign in to the system.
As a user, I want to create Game |  |  | As a user, I want to create Game
As a user, I want to Invite another player |  |  | As a user, I want to Invite another player
As a user, I want to accept the game invitation |  |  | As a user, I want to accept the game invitation
As a user, I want to reject the game invitation |  |  | As a user, I want to reject the game invitation
As a user, I want to move as per the rules while playing in the game. |  |  | As a user, I want to move as per the rules while playing in the game.

## 10-7 - 10-13
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
| As a user, I want to register to the system |  |  | As a user, I want to register to the system
| As a user, I want to sign in to the system. |  |  | As a user, I want to sign in to the system.
As a user, I want to create Game |  |  | As a user, I want to create Game
As a user, I want to Invite another player |  |  | As a user, I want to Invite another player
As a user, I want to accept the game invitation |  |  | As a user, I want to accept the game invitation
As a user, I want to reject the game invitation |  |  | As a user, I want to reject the game invitation
As a user, I want to move as per the rules while playing in the game. |  |  | As a user, I want to move as per the rules while playing in the game.

## 10-14 - 10-20
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
| As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
| As a user, I want to sign in to the system. |  |  |  | As a user, I want to sign in to the system.
As a user, I want to create Game |  |  | As a user, I want to create Game
As a user, I want to Invite another player |  |  | As a user, I want to Invite another player
As a user, I want to accept the game invitation |  |  | As a user, I want to accept the game invitation
As a user, I want to reject the game invitation |  |  | As a user, I want to reject the game invitation
As a user, I want to move as per the rules while playing in the game. |  |  | As a user, I want to move as per the rules while playing in the game.

## 10-21 - 10-27
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
|  | As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
|  | As a user, I want to sign in to the system. |  |  |  |  | As a user, I want to sign in to the system.
As a user, I want to create Game |  |  | As a user, I want to create Game
| As a user, I want to Invite another player |  |  | As a user, I want to Invite another player
As a user, I want to accept the game invitation |  |  | As a user, I want to accept the game invitation
As a user, I want to reject the game invitation |  |  | As a user, I want to reject the game invitation
| As a user, I want to move as per the rules while playing in the game. |  |  | As a user, I want to move as per the rules while playing in the game.

## 10-28 - 11-3
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
|  | As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
|  | As a user, I want to sign in to the system. |  |  |  |  | As a user, I want to sign in to the system.
| As a user, I want to create Game |  |  | As a user, I want to create Game
| As a user, I want to Invite another player |  |  |  | As a user, I want to Invite another player
| As a user, I want to accept the game invitation |  |  | As a user, I want to accept the game invitation
| As a user, I want to reject the game invitation |  |  | As a user, I want to reject the game invitation
| As a user, I want to move as per the rules while playing in the game. |  |  | As a user, I want to move as per the rules while playing in the game.

## 11-4 - 11-11
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
|  | As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
|  | As a user, I want to sign in to the system. |  |  |  |  | As a user, I want to sign in to the system.
|  | As a user, I want to create Game |  |  |  |  | As a user, I want to create Game
|  | As a user, I want to Invite another player |  |  |  |  | As a user, I want to Invite another player
As a user, I want to accept the game invitation |  |  | As a user, I want to accept the game invitation
As a user, I want to reject the game invitation |  |  | As a user, I want to reject the game invitation
|  | As a user, I want to move as per the rules while playing in the game. |  |  |  |  | As a user, I want to move as per the rules while playing in the game.
As a user, I want to quit the game |  |  | As a user, I want to quit the game
As a user, I want to unregister from the system |  |  | As a user, I want to unregister from the system
As a user, I want to see the list of all active games |  |  | As a user, I want to see the list of all active games
As a user, I want to switch between active games |  |  | As a user, I want to switch between active games
As a user, I want to log out from the system. |  |  | As a user, I want to log out from the system.
As a user, I want to see the user-profiles. |  |  | As a user, I want to see the user-profiles.
As a user, I want to see history of the played games |  |  | As a user, I want to see history of the played games