## Sprint 01
Sprint Tasks | Date | Participants | Minutes of Meeting (MoM)
Sprint Planning | 9/09/2019 (Monday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Got acquinted with the team. 2. Decided that Rachit Dalal will be the Scrum Master 3. Discussed about how tasks should be divided among the three Sprints.
Daily Scrum 01 | 9/11/2019 (Wednesday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Requirement Elicitation:- After reading the problem statement, we wrote down the user requirements we understood individually and then made a "Problem Definition" document. 2. Decided to gather more information on the game Banqi and present it during the next Scrum Meeting.
Daily Scrum 02 | 9/16/2019 (Monday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Requirement Evolution:- After gathering more information on the game Banqi, we edited the Problem Definition document to add information about Banqi. 2. Scrum Master created the GitHub repository - cs414-f18-001-sparkans 3. Had a technical discussion and decided on the technical aspects
Daily Scrum 03 | 9/18/2019 (Wednesday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Discussed about the different epics we created and decided on how to break down these epics to user stories.
Daily Scrum 04 | 9/23/2019 (Monday) | 1. Dr. Laura Moreno (PO) 2. Nisha Rani 3. Rachit Dalal 4. Sushant Patankar 5. Swathy Hari Prasad | 1. Discussion with Product Owner to review the user stories.
Daily Scrum 05 | 9/25/2019 (Wednesday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Completed the user stories and wrote the various Acceptance Criteria for each user story.
Sprint Review | 9/26/2019 (Thursday) | 1. Dr. Laura Moreno (PO) 2. Nisha Rani 3. Rachit Dalal 4. Sushant Patankar 5. Swathy Hari Prasad | 1. Product Owner reviewed the user stories and suggested some changes. 2. Product Owner assigned priorities to all the user stories according to MoSCow Rule.
Daily Scrum 06 | 9/27/2019 (Friday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Edited the user stories as per Prodcut Owner's suggestion 2. Created User tasks for Must have user stories. 3. Created CRC cards and Class Diagrams for Must have user stories.
Sprint Retrospective | 9/28/2019 (Saturday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Decided Technical Aspects: * Front-end : jSwing / Angular JS * Database : MySQL 2. Reviewed the CRC cards and Class diagrams for the Must have user stories. 3. Completed Requirement gathering and created user stories

## Sprint 02
Sprint Tasks | Date | Participants | Minutes of Meeting (MoM)
Sprint Planning | 10/09/2019 (Wednesday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Identified different user stories and user tasks that should be taken up in the second sprint.
Daily Scrum 01 | 10/14/2019 (Monday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Finalized on the technologies that should be used on the server and client side. 2. Had a discussion on how to establish the client-server communication.
Daily Scrum 02 | 10/17/2019 (Thursday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Completed the code set up. 2. Discussed the different technical aspects. 3. Worked on establishing the client-server communication.
Daily Scrum 03 | 10/21/2019 (Monday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Completed the CRC cards and Class diagrams for the user stories. 2. Discussed on the changes to be made in the middle tier in order to coomunicate with the front end
Daily Scrum 04 | 10/24/2019 (Wednesday) | 1. Dr. Laura Moreno (PO) 2. Rachit Dalal 3. Nisha Rani 4. Sushant Patankar 5. Swathy Hari Prasad 6. Derek Chapman | 1. Discussion with Product Owner to review the work and took an appointment for Sprint review. 2. Completed different user tasks and their integration.
Daily Scrum 05 | 10/28/2019 (Monday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Establised client-server communication. 2. Worked on integrating the front-end, back-end and database.
Daily Scrum 06 | 10/30/2019 (Wednesday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Worked on integration of all the parts. 2. Code modifications done.
Sprint Review | 10/31/2019 (Thursday) | 1. Dr. Laura Moreno (PO) 2. Nisha Rani 3. Rachit Dalal 4. Sushant Patankar 5. Swathy Hari Prasad 6. Derek Chapman | 1. Met the Product Owner to show the demo. 2. Product Owner suggested some changes which will be implemted if time permits.
Daily Scrum 07 | 11/1/2019 (Friday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Code refactoring. 2. Code Modifications. 3. Integration of all parts.
Sprint Retrospective | 11/2/19 (Saturday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | What went well: 1. Co-ordination among team members helped towards stabilization. 2. Using Excel sheets for tracking made it easier. 3. Tried improving quality during each integration. 4. After each scrum meeting, code refactoring was performed. Need to improve: 1. Equal distribution of work is required going forward. 2. We underestimated many tasks. 3. More importance given to functionalities than aesthetics.

## Sprint 03
Sprint Tasks | Date | Participants | Minutes of Meeting (MoM)
Sprint Planning | 11/06/2019 (Wednesday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Identified different user stories and user tasks that should be taken up in the third sprint and had a discussion about its implementation
Daily Scrum 01 | 11/1119 (Monday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Completed the CRC cards and Class diagrams for the user stories. 2. Discussed on the changes to be made in the existing code to get the game working.
Daily Scrum 02 | 11/14/2019 (Thursday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Code refactoring done for existing code and tested the working of existing functionalities.
Daily Scrum 03 | 11/18/2019 (Monday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Modified the existing code to include more functionalities according to the requirements.
Daily Scrum 04 | 11/20/2019 (Wednesday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Identified some bugs in the Invitation part and decided on the priority of tasks to be done during Thanksgiving break.
Sprint Review | 11/22/2019 (Friday) | 1. Dr. Laura Moreno (PO) 2. Nisha Rani 3. Rachit Dalal 4. Sushant Patankar 5. Swathy Hari Prasad 6. Derek Chapman | 1. Met the Product Owner to discuss the priorities and also to get a feedback on the P2.
Daily Scrum 05 | 11/26/2019 (Tuesday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Code refactoring. 2. Code Modifications. 3. Added new functionalities.
Daily Scrum 06 | 12/2/2019 (Monday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Code refactoring. 2. Code Modifications. 3. Added new functionalities.
Daily Scrum 07 | 12/5/2019 (Thursday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | 1. Code refactoring. 2. Code Modifications. 3. Integrating all the sections to get a working game.
Sprint Retrospective | 12/7/19 (Saturday) | 1. Rachit Dalal 2. Nisha Rani 3. Sushant Patankar 4. Swathy Hari Prasad 5. Derek Chapman | What went well: 1. Co-ordination and equal work distribution among team members made this sprint much easier. 2. Using Excel sheets for tracking made tracking easier. 3. Tried improving quality during each integration. 4. Code refactoring was performed. 5. Unit test cases implemented effectively. 6. Aesthetics of UI is taken care of