## User Story
Story Number | Title | Acceptance Criteria | Priority | Estimate | Doubt
1 | As a user, I want to register to the system | 1. User enters unique and valid email, nickname and password. 1. A valid email should be entered which is unique. 2. Nickname should be unique. 3. Password should follow password criterias. 2. When all validations pass, Register button is enabled. 3. Data is stored in the database tables with status as Active. | Must have
2 | As a user, I want to sign in to the system. | 1. When the user enters the nickname and password, the Sign In button should be activated. 2. On clicking the sign in button, the nickname and password combination is validated against the database table. 3. If the database validation result is true, the user will be able to log in to the system. 4. If the database validation is false and nickname exists in the database, the user will be prompted to enter correct password. 5. If the database validation is false and nickname doesnot exist in the database table, user will be prompted to register. | Must have
3 | As a user, I want to create Game | 1. A registered user can create a new game. 2. The same user can send more than one invitation to other users to start the game. 3. From all the invited users, only one can join the game on a first come first serve basis. 4. As soon as a user joins the invitation, the game will be ready to start. 5. The users are notified that the game has statrted. 6. The system marks the game as active and no other user can join the game. | Should have
4 | As a user, I want to Invite another player | 1. User invites another user using valid username. 2. Invitation link/notification should be sent to the invited user. 3. User can send as many invitation as he wants. | Should have
5 | As a user, I want to accept the game invitation | 1. Invitee accept the game invitation through Accept link. 2. An Acceptance notification is send to the inviter. | Should have
6 | As a user, I want to reject the game invitation | 1. User can reject the game invitation. 2. Invited user Rejects the invitation. 3. The user is notified of invited user's rejection. | Should have
7 | As a user, I want to quit the game | 1. User can opt to leave an in-progress game by selecting the quit option. 2. When the user clicks on Quit button, he should be removed from that game. 3. The system notifies both users that the game has been successfully ended. 4. The status of that game should be updated "Withdrawn" in the database table for the user who quit the game. 5. Opponent will automatically win the game. | Could have |  | What should be the status for oppenent ?
8 | As a user, I want to unregister from the system | 1. The user selects to unregister from his account. 2. The system logs out the user. 3. All the active and inactive games should be ended. 4. User account should be deleted from the system. | Could have
9 | As a user, I want to move as per the rules while playing in the game. | 1. User moves a piece on his turn. 2. User can make a legal move. 3. For any wrong move system will notify the user. 4. Once user makes move the system notifies the opponent that it is your turn. | Should have
10 | As a user, I want to see the list of all active games | 1. User should be able to see all the active games that he has joined before. 2.
11 | As a user, I want to switch between active games | 1. User can select one of their saved games to sart playing. 2. The game should start from the saved state. 3. User can make the move as per the rules. 4. User can play till the game ends. 5. User can leave the game instance as well. 6. The system stores the game state once user leaves the game. | Could have
12 | As a user, I want to log out from the system. | 1. When the user clicks on the Log Off button, user should be able to log off from the game. 2. If the user logged off in between the game, then game status is stored in the database. 3. If the user logged off after the game is finished, then the game result is stored in the database. | Could have
13 | As a user, I want to see the user-profiles. | 1. When the registered user clicks on the profile, he should be able to see the history of all played games along with statistics of Win/Loss/ Withdrawn related to the name. | Wont have until later
14 | As a user, I want to see history of the played games | 1. When a game is over, the result of the game (Won/Lost/Withdrawn) and other details like name of players, start date, end date and times are stored in the database. 2. When a game is paused, the state of that game is stored in the database. 3. When a game is abandoned, details of that game stored in the database along with its status. | Wont have until later

## User Tasks
| User Story | Tasks | Validations | DB Entry
Create CRC Cards
Create Class Diagram
1 | As a user, I want to register to the system | The Registration page should have a text box to enter nickname with a side text "Enter Nickname:" | 1. Nickname should be unique - should be validated against the database table "User". 2. Nickname cannot contain special characters other than period and underscore 3. Nickname should be a minimum of 8 characters and can be a maximum of 16 characters
|  | The Registration page should have a password form element to enter the password with a side text "Enter Password:". | 1. Case sensitive 2. Should have a minimum of 8 characters 3. Should contain special characters 4. Should contain at-least one capital alphabet
|  | The Registration page should have a password form element to enter the password with a side text "Confirm Password:". | 1. Password should be same as the one entered in the "Enter Password" text.
|  | The Registration page should have a text box to enter email id with a side text "Enter Email id:". | 1. Javascript validation to enter a valid email with all email id criterias. 2. Email should be unique.
|  | The Registration page should have "Register Now" button | 1. If all the above validations of nickname, password and email id pass, the button is enabled. | Nickname, password and email id details are stored in the database table "User".
Create CRC Cards
Create Class Diagram
2 | As a user, I want to sign in to the system. | The Sign In page should have a text box to enter nickname
The Sign In page should have a password form element to enter the password
|  | The Sign In page should have "Sign In" button. | 1. The nickname and password entered are validated against the database table "User" and if the validations pass, the Sign In button is enabled. 2. If the database validations fail and username does not exist, user is promted to Register. 3. If the database validation fails and nickname exists in the database, the user will be prompted to enter correct password | The user status in "User" table is updated to Active.
|  | The Sign In page should have a "Register Here" button. | 1. On clicking this button, user is taken to Registration Page.

## Output of Scrum Ceremony
Sprint Tasks | Date | Participants | Minutes of Meeting (MoM)
Sprint Planning | 9/09/2019 (Monday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Got acquinted with the team. 2. Decided that Rachit Dalal will be the Scrum Master 3. Discussed about how tasks should be divided among the three Sprints.
Daily Scrum 01 | 9/11/2019 (Wednesday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Requirement Elicitation:- After reading the problem statement, we wrote down the user requirements we understood individually and then collectively made a "Problem Definition" document. 2. Decided to gather more information on the game Banqi and present it during the next Scrum Meeting.
Daily Scrum 02 | 9/16/2019 (Monday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Requirement Evolution:- After gathering more information on the game Banqi, we edited the Problem Definition document to add information about Banqi. 2. Scrum Master created the GitHub repository - cs414-f18-001-sparkans 3. Had a technical discussion and decided on the technical aspects
Daily Scrum 03 | 9/18/2019 (Wednesday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Discussed about the different epics we created and decided on how to break down these epics to user stories.
Daily Scrum 04 | 9/23/2019 (Monday) | 1. Dr. Laura Moreno (PO) 2. Nisha Rani 3. Rachit Dalal 4. Sushant Patankar 5. Swathy Hari Prasad | 1. Discussion with Product Owner to check if the user stories are in the correct format
Daily Scrum 05 | 9/25/2019 (Wednesday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Completed the user stories and wrote the various Acceptance Criteria for each user story.
Sprint Review | 9/26/2019 (Thursday) | 1. Dr. Laura Moreno (PO) 2. Nisha Rani 3. Rachit Dalal 4. Sushant Patankar 5. Swathy Hari Prasad | 1. Product Owner reviewed the user stories and suggested some changes. 2. Product Owner assigned priorities to all the user stories according to MoSCow Rule.
Daily Scrum 06 | 9/27/2019 (Friday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Edited the user stories as per Prodcut Owner's suggestion 2. Created User tasks for Must have user stories. 3. Created CRC cards and Class Diagrams for Must have user stories.
Sprint Retrospective | 9/28/2019 (Saturday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Decided Technical Aspects: * Front-end : jSwing / Angular JS * Database : MySQL 2. Reviewed the CRC cards and Class diagrams for the Must have user stories. 3. Completed Requirement gathering and created user stories

## Kanban Board for Sprint 2
Kanban Board for Sprint 2
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
| User Story 01 |  |  | User Story 01
User Story 03 |  |  | User Story 03
| User Story 02 |  |  | User Story 02
User Story 04 |  |  | User Story 04
User Story 05 |  |  | User Story 05
User Story 06 |  |  | User Story 06
User Story 09 |  |  | User Story 09

## Sheet6
Kanban Board for Sprint 1
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
| User Story 01 |  | User Story 01
User Story 03 |  |  | User Story 02
| User Story 02 |  | User Story 03
User Story 04 |  |  | User Story 04
User Story 05 |  |  | User Story 05
User Story 06 |  |  | User Story 06
User Story 09 |  |  | User Story 09
Story No | Title
1 | As a team, we want to discuss and finalize technology stack to develop the game.
2 | As a team, we want to have github reposatory setup.
3 | As a team, we will understand the problem statement and the game banqi and its rules.

## Form responses 1
Timestamp | Untitled Question