## 9 16 - 9 22
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
| As a user, I want to register to the system |  | As a user, I want to register to the system
As a user, I want to sign in to the system. |  |  | As a user, I want to sign in to the system.

## 9 23 - 9 29
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
| As a user, I want to register to the system |  | As a user, I want to register to the system
As a user, I want to create Game |  |  | As a user, I want to sign in to the system.
| As a user, I want to sign in to the system. |  | As a user, I want to create Game
As a user, I want to Invite another player |  |  | As a user, I want to Invite another player
As a user, I want to accept the game invitation
As a user, I want to accept the game invitation |  |  | As a user, I want to reject the game invitation
As a user, I want to move as per the rules while playing in the game.
As a user, I want to reject the game invitation
As a user, I want to move as per the rules while playing in the game.
* Completed the CRC cards and Class diagrams for User Story 01 and User Story 02.

## 9 30 - 10 6
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
As a user, I want to register to the system |  |  | As a user, I want to register to the system
As a user, I want to sign in to the system. |  |  | As a user, I want to sign in to the system.
As a user, I want to create Game |  |  | As a user, I want to create Game
As a user, I want to Invite another player |  |  | As a user, I want to Invite another player
As a user, I want to accept the game invitation |  |  | As a user, I want to accept the game invitation
As a user, I want to reject the game invitation |  |  | As a user, I want to reject the game invitation
As a user, I want to move as per the rules while playing in the game. |  |  | As a user, I want to move as per the rules while playing in the game.

## 10 7 - 10 13
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
| As a user, I want to register to the system |  |  | As a user, I want to register to the system
| As a user, I want to sign in to the system. |  |  | As a user, I want to sign in to the system.
As a user, I want to create Game |  |  | As a user, I want to create Game
As a user, I want to Invite another player |  |  | As a user, I want to Invite another player
As a user, I want to accept the game invitation |  |  | As a user, I want to accept the game invitation
As a user, I want to reject the game invitation |  |  | As a user, I want to reject the game invitation
As a user, I want to move as per the rules while playing in the game. |  |  | As a user, I want to move as per the rules while playing in the game.

## 10 14 - 10 20
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
| As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
| As a user, I want to sign in to the system. |  |  |  | As a user, I want to sign in to the system.
As a user, I want to create Game |  |  | As a user, I want to create Game
As a user, I want to Invite another player |  |  | As a user, I want to Invite another player
As a user, I want to accept the game invitation |  |  | As a user, I want to accept the game invitation
As a user, I want to reject the game invitation |  |  | As a user, I want to reject the game invitation
As a user, I want to move as per the rules while playing in the game. |  |  | As a user, I want to move as per the rules while playing in the game.

## 10 21 - 10 27
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
|  | As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
|  | As a user, I want to sign in to the system. |  |  |  |  | As a user, I want to sign in to the system.
As a user, I want to create Game |  |  | As a user, I want to create Game
| As a user, I want to Invite another player |  |  | As a user, I want to Invite another player
As a user, I want to accept the game invitation |  |  | As a user, I want to accept the game invitation
As a user, I want to reject the game invitation |  |  | As a user, I want to reject the game invitation
| As a user, I want to move as per the rules while playing in the game. |  |  | As a user, I want to move as per the rules while playing in the game.

## 10 28 - 11 3
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
|  | As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
|  | As a user, I want to sign in to the system. |  |  |  |  | As a user, I want to sign in to the system.
|  | As a user, I want to create Game |  |  |  |  | As a user, I want to create Game
|  | As a user, I want to Invite another player |  |  |  |  | As a user, I want to Invite another player
|  | As a user, I want to accept the game invitation |  |  |  |  | As a user, I want to accept the game invitation
|  | As a user, I want to reject the game invitation |  |  |  |  | As a user, I want to reject the game invitation
| As a user, I want to move as per the rules while playing in the game. |  |  |  | As a user, I want to move as per the rules while playing in the game.

## 11 4 - 11 10
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
|  | As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
|  | As a user, I want to sign in to the system. |  |  |  |  | As a user, I want to sign in to the system.
|  | As a user, I want to create Game |  |  |  |  | As a user, I want to create Game
|  | As a user, I want to Invite another player |  |  |  |  | As a user, I want to Invite another player
|  | As a user, I want to accept the game invitation |  |  |  |  | As a user, I want to accept the game invitation
|  | As a user, I want to reject the game invitation |  |  |  |  | As a user, I want to reject the game invitation
| As a user, I want to move as per the rules while playing in the game. |  |  |  | As a user, I want to move as per the rules while playing in the game.
| As a user, I want to quit the game |  |  | As a user, I want to quit the game
| As a user, I want to unregister from the system |  |  | As a user, I want to unregister from the system
As a user, I want to log out from the system. |  |  | As a user, I want to log out from the system.
As a user, I want to see the user-profiles. |  |  | As a user, I want to see the user-profiles.
As a user, I want to see history of the played games |  |  | As a user, I want to see history of the played games
As a user, I want to save the game. |  |  | As a user, I want to save the game.

## 11 11 - 11 17
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
|  | As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
|  | As a user, I want to sign in to the system. |  |  |  |  | As a user, I want to sign in to the system.
|  | As a user, I want to create Game |  |  |  |  | As a user, I want to create Game
|  | As a user, I want to Invite another player |  |  |  |  | As a user, I want to Invite another player
|  | As a user, I want to accept the game invitation |  |  |  |  | As a user, I want to accept the game invitation
|  | As a user, I want to reject the game invitation |  |  |  |  | As a user, I want to reject the game invitation
| As a user, I want to move as per the rules while playing in the game. |  |  | As a user, I want to move as per the rules while playing in the game.
| As a user, I want to quit the game |  |  | As a user, I want to quit the game
| As a user, I want to unregister from the system |  |  | As a user, I want to unregister from the system
As a user, I want to log out from the system. |  |  | As a user, I want to log out from the system.
As a user, I want to see the user-profiles. |  |  | As a user, I want to see the user-profiles.
As a user, I want to see history of the played games |  |  | As a user, I want to see history of the played games
As a user, I want to save the game. |  |  | As a user, I want to save the game.

## 11 18 - 11 24
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
|  | As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
|  | As a user, I want to sign in to the system. |  |  |  |  | As a user, I want to sign in to the system.
|  | As a user, I want to create Game |  |  |  |  | As a user, I want to create Game
| As a user, I want to Invite another player |  |  |  | As a user, I want to Invite another player
|  | As a user, I want to accept the game invitation |  |  |  |  | As a user, I want to accept the game invitation
|  | As a user, I want to reject the game invitation |  |  |  |  | As a user, I want to reject the game invitation
| As a user, I want to move as per the rules while playing in the game. |  |  |  | As a user, I want to move as per the rules while playing in the game.
| As a user, I want to quit the game |  |  | As a user, I want to quit the game
| As a user, I want to unregister from the system |  |  | As a user, I want to unregister from the system
As a user, I want to log out from the system. |  |  | As a user, I want to log out from the system.
As a user, I want to see the user-profiles. |  |  | As a user, I want to see the user-profiles.
As a user, I want to see history of the played games |  |  | As a user, I want to see history of the played games
As a user, I want to save the game. |  |  | As a user, I want to save the game.

## 11 25 - 12 01
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
|  | As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
|  | As a user, I want to sign in to the system. |  |  |  |  | As a user, I want to sign in to the system.
|  | As a user, I want to create Game |  |  |  |  | As a user, I want to create Game
| As a user, I want to Invite another player |  |  |  |  | As a user, I want to Invite another player
|  | As a user, I want to accept the game invitation |  |  |  |  | As a user, I want to accept the game invitation
|  | As a user, I want to reject the game invitation |  |  |  |  | As a user, I want to reject the game invitation
| As a user, I want to move as per the rules while playing in the game. |  |  |  | As a user, I want to move as per the rules while playing in the game.
| As a user, I want to quit the game |  |  | As a user, I want to quit the game
|  | As a user, I want to unregister from the system |  |  |  |  | As a user, I want to unregister from the system
|  | As a user, I want to log out from the system. |  |  |  |  | As a user, I want to log out from the system.
As a user, I want to see the user-profiles. |  |  | As a user, I want to see the user-profiles.
As a user, I want to see history of the played games |  |  | As a user, I want to see history of the played games
As a user, I want to save the game. |  |  | As a user, I want to save the game.

## 12 02 - 12 08
To - do | Doing | Done | To - do | In Dev | Testing | Code Review | Done
|  | As a user, I want to register to the system |  |  |  |  | As a user, I want to register to the system
|  | As a user, I want to sign in to the system. |  |  |  |  | As a user, I want to sign in to the system.
|  | As a user, I want to create Game |  |  |  |  | As a user, I want to create Game
|  | As a user, I want to Invite another player |  |  |  |  | As a user, I want to Invite another player
|  | As a user, I want to accept the game invitation |  |  |  |  | As a user, I want to accept the game invitation
|  | As a user, I want to reject the game invitation |  |  |  |  | As a user, I want to reject the game invitation
|  | As a user, I want to move as per the rules while playing in the game. |  |  |  |  | As a user, I want to move as per the rules while playing in the game.
|  | As a user, I want to quit the game |  |  |  |  | As a user, I want to quit the game
|  | As a user, I want to unregister from the system |  |  |  |  | As a user, I want to unregister from the system
|  | As a user, I want to log out from the system. |  |  |  |  | As a user, I want to log out from the system.
|  | As a user, I want to see the user-profiles. |  |  |  |  | As a user, I want to see the user-profiles.
|  | As a user, I want to see history of the played games |  |  |  |  | As a user, I want to see history of the played games
|  | As a user, I want to save the game. |  |  |  |  | As a user, I want to save the game.