## Output of Scrum Ceremonies
Sprint Tasks | Date | Participants | Minutes of Meeting (MoM)
Sprint Planning | 9/09/2019 (Monday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Got acquinted with the team. 2. Decided that Rachit Dalal will be the Scrum Master 3. Discussed about how tasks should be divided among the three Sprints.
Daily Scrum 01 | 9/11/2019 (Wednesday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Requirement Elicitation:- After reading the problem statement, we wrote down the user requirements we understood individually and then made a "Problem Definition" document. 2. Decided to gather more information on the game Banqi and present it during the next Scrum Meeting.
Daily Scrum 02 | 9/16/2019 (Monday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Requirement Evolution:- After gathering more information on the game Banqi, we edited the Problem Definition document to add information about Banqi. 2. Scrum Master created the GitHub repository - cs414-f18-001-sparkans 3. Had a technical discussion and decided on the technical aspects
Daily Scrum 03 | 9/18/2019 (Wednesday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Discussed about the different epics we created and decided on how to break down these epics to user stories.
Daily Scrum 04 | 9/23/2019 (Monday) | 1. Dr. Laura Moreno (PO) 2. Nisha Rani 3. Rachit Dalal 4. Sushant Patankar 5. Swathy Hari Prasad | 1. Discussion with Product Owner to review the user stories.
Daily Scrum 05 | 9/25/2019 (Wednesday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Completed the user stories and wrote the various Acceptance Criteria for each user story.
Sprint Review | 9/26/2019 (Thursday) | 1. Dr. Laura Moreno (PO) 2. Nisha Rani 3. Rachit Dalal 4. Sushant Patankar 5. Swathy Hari Prasad | 1. Product Owner reviewed the user stories and suggested some changes. 2. Product Owner assigned priorities to all the user stories according to MoSCow Rule.
Daily Scrum 06 | 9/27/2019 (Friday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Edited the user stories as per Prodcut Owner's suggestion 2. Created User tasks for Must have user stories. 3. Created CRC cards and Class Diagrams for Must have user stories.
Sprint Retrospective | 9/28/2019 (Saturday) | 1. Nisha Rani 2. Rachit Dalal 3. Sushant Patankar 4. Swathy Hari Prasad | 1. Decided Technical Aspects: * Front-end : jSwing / Angular JS * Database : MySQL 2. Reviewed the CRC cards and Class diagrams for the Must have user stories. 3. Completed Requirement gathering and created user stories